## Event Planning Timeline
TIME FRAME | EVENT ITEM | SPECIFIC TASKS & RESPONSIBILITIES | COMMENTS/NOTES
7-8 MONTHS | Initial Planning | Schedule initial concept meeting with key stakeholders (EAR, IT, MarCom, Fiscal Team, Facilities/Operations) to discuss the event in general, articulate purpose and goals; target audience; audience size; event format; speaker(s); technology needs; resources needed (staffing, budget, etc.); desired dates; etc.
7-8 MONTHS | Initial Planning | As soon as you have an event to produce, and know that you will need to enlist School partners in support of the event, the first step is to complete and submit the EVENT INTAKE FORM located on the School of Business Event Management website (link at right). The information provided ensures the next step is more efficient, effective, and that the right people are included. | https://www.business.uconn.edu/events/planning-your-event/
|  | Schedule initial concept meeting with key supporting stakeholders -- E&AE, IT, MarCom, Fiscal Team, Development, Facilities/Ops -- to discuss event in general, articulate purpose, goals; target audience and size; date; event format; speaker(s); technology needs; space needs; other resources needed (staffing, budget, etc.). | Note: supporting stakeholders are color coded as referenced throughout this document. See Points of Contact tab below for specific representatives of each.
Review all planning resources located on the School of Business Event Management website (link above right). This includes various guidelines and checklists to help you coordinate with supporting stakeholders.
Assemble an event committee, beginning with appointing a primary “point of contact” (POC) from the requesting program/office/dept. The POC is the event owner and project manager, keeping everyone and everything on track. The balance of the committee should include members from each support service provider contributing to the development, production, execution, and success of the event.
5-6 MONTHS | Event Date/ Calendar | Finalize event date and submit confirmed event date to appropriate event calendars including Dean, faculty, departments, etc. (See Event Management website resources for guidelines on how to add event to University Events Calendars.) Consult w/ Dean's Executive Assistant (Tina Pierce) for setting dates if President or Provost is to be invited.
| Financial (Budget) | Create event budget, forecasting cost estimates such as room/facility rental, equipment rental or purchase, catering (food, beverage, etc.), speaker/entertainment fees (including lodging and travel), photography and/or filming, permit/licenses/insurance fees, flowers, finishing details, swag, parking fees, etc. Consult Fiscal Team as needed.
Will there be registration fee(s)? If so, confirm fee(s) and contact the Fiscal Team to obtain a form to create a registration page that will process payment through the University's "Marketplace" platform; if no money is being collected, a simple registration form is sufficient (more info below).
Process required Foundation pre-approval related to alcoholic beverages. You can ask your Dept. Admin. or Carleen Morneau for a copy of the form.
| Event Venue | Identify desired venue(s). If venue is estimated to be over $10K, an RFP (request for proposal) is usually required and evaluated; if selected venue is other than the lowest bidder, a justification is required.
|  | If approved venue is a "new vendor," the vendor must submit a New Vendor Form and a W-9 form through HuskyBuy (see link). | https://purchasing.ubs.uconn.edu/
Schedule and complete site visit(s), including Facilities, IT, and others as needed.
Once contract is awarded, confirm/reserve date with venue and forward all paperwork to Fiscal Team for processing, including: pre-approval forms, purchase requisitions, contracts, advances, etc.
Create purchase requisition for venue, including other venue-related items that need to be purchased or rented such as tables, chairs, linens, A/V, etc.
If there's a BEO (banquet event order) or any payment (or promise to pay) paperwork, forward to fiscal designee for processing. NOTE: staff are not allowed to sign anything that commIT the University; in lieu of signing a vendor's form(s), simply refer to the issued P.O. (purchase order) as UConn's guarantee of payment.
If alcohol is being served at the event, a separate quote is required. NOTE: alcoholic beverages cannot be paid for with University funds. Consult with Development Office to determine if a UConn Foundation account may be used.
|  | If event is out of state, faculty/staff must submit a Travel Authorization form via Concur. | https://travel.uconn.edu/
If event A/V is to be outsourced, provide IT with technical points-of-contact for the outside vendors.
| Sponsorship | If sponsors are being solicited, consult with Development Office to identify sponsorship opportunities, finalize levels and dollar amounts; be clear as to what the benefit/deliverables are for each sponsorship level.
As sponsors are committed and signed, request logos and pertinent information for sponsor promotion and acknowledgement.
| Speaker(s)/VIP Guests | Identify and confirm speakers/presenters/moderator/entertainers/etc. as appropriate; identify a VIP coordinator or "handler". Consult w/ E&AE if assistance is needed in securing alumni and/or corporate individuals for these roles (submit request via link). | https://alumni.business.uconn.edu/events/engagement-request-form/
If University President or Provost is to be invited, please coordinate event date and invitations through the Dean's Office (Exec. Assistant Tina Pierce). If Governor or any other political/government VIP's are to be invited, please also coordinate with Dean's office and University Government Affairs office.
| MarCom | Work with MarCom office to develop a marketing strategy (promotional opportunities, collateral design, printing, signage, social media, media relations, etc.) and, if needed, create event-branded assets; identify cross-promotional opportunities with other groups.
Create a Facebook event page and leverage other program-owned social media channels; generate buzz on blogs, member forums, social channels, etc.; consult with MarCom as needed.
Build out event web pages featuring and promoting the event. Consult w/ MarCom if necessary.
Create and link registration page(s) - reminder: if money is being collected, consult w/ fiscal team to build registration through UConn's Marketplace platform; otherwise, creating a simple registration form/page is sufficient.
Announce early-bird registration, if appropriate.
Send printed and/or electronic "save the date" to invitees.
| IT | If being used, consult with IT to determine appropriate platform for streaming, recording, and set up event links.
3-4 MONTHS | Speaker(s) | Confirm speaker/presenter/moderator/entertainers/etc.; brief participants on the event; secure bio information, photos, etc.
Finalize presentation/speech topics; draft excerpt for promotion.
|  | Work on travel and accommodation arrangements; consult university travel policies (see link). | https://travel.uconn.edu/
Have contracts (incuding photo/content releases) signed by both parties.
| Venue | Discuss and arrange all details such as menu, linens, staffing, layout and staging, A/V equipment (enlist IT support as needed), parking, signage, registration set-up, etc. (enlist Facilities/Ops. as needed).
Provide IT with preferred room layout of seating and tables for audience, speakers and panelists, catering, etc.
Identify and secure any special permit, licenses, insurance, security, etc., consulting Facilities/Ops as needed.
Ensure accessibility requirements, consulting Facilities/Ops as needed.
Review event security needs/plan with venue manager, consulting Facilities/Ops if needed.
| MarCom | Four months prior, detailed copy/text should be drafted and forwarded to MarCom for the design of promotional pieces such as newsletter promos, ads, radio spots, releases to media publications and other outlets, etc.; materials should undergo rounds of editing on a rolling basis.
If printed program and/or event signage is needed, provide all information to be included to MarCom for design; consult w/ MarCom on printing re: design file submission.
Secure vendor quotes and purchase orders for any printing needs; facilitate the interaction between the printer and MarCom to submit design files; carefully review and proofread all printer proofs and give final approval for printing.
To the extent possible, all printed pieces, with the exception of the event program perhaps, should be printed by the 1 1/2 month mark.
| Admin. | Address, stuff, stamp invitations for physical mailing.
Identify VIP audience and coordinate special invitation, discount codes, etc., and monitor engagement.
Engage venue facilities/ops group to arrange parking details (if venue is not UConn).
Order desired event swag/speaker gifts/promo items, etc.
1-2 MONTHS | Speaker(s) | Confirm travel and accommodation details.
Request copy of speeches and/or presentations. Plan PowerPoint and projection of audio/visual content if needed
| Venue | On-site visit for coordination of all event elements.
Meet with IT for any final adjustments to technical support or A/V needs. In coordination with MarCom, inform IT whether any press will be onsite, and provide contacts for IT to determine individual technical requirements.
| Sponsorship | Follow up to confirm sponsorships, coordinating with Development Office as needed; ensure deliverables are in place for the sponsor; secure any sponsor promotional materials to be shared at the event.
Ask sponsors to promote their sponsorship participation on their social media channels and other promotional outlets.
| Registration | Close early-bird registration; promote general pricing.
Export RSVP list weekly and forward to key people as appropriate (dean and associate deans, development team, E&AE, etc.) For Marketplace RSVP lists, consult with Fiscal Team/Rachel Greene.
Ask the Development Office for applicable attendees such as VIPs, featured host(s), judges, panelists, keynote speakers, high-level administrators, and anyone of relevant importance to the event. If attendee is not in Felix, the event owner is responsible for drafting a mini-bio as needed.
Select staff for reception table and assign point person.
| MarCom | Send event reminders to contact list(s), to secure additional RSVPs.
Work w/ MarCom to release press announcements re: keynote speakers, celebrities, honorees, VIPs, etc.
Publish pre-event news release on your website and circulate to all partners, affiliated organizations, etc.; continue promoting event on social media.
Work w/ MarCom to finalize and carefully proofread printed program (and any remaining materials) prior to printing.
Consult with Mar/Com to plan and schedule event photographer if needed.
| IT | Work with IT to connect with outsourced vendors and press regarding technical requirements, layout and setup schedule, and other needs.
Provide IT with contact info. for any remote speakers/presenters for scheduling test calls and coordinating event invitations.
1-2 WEEKS | Admin. | Hold final meeting w/ event committee to review all details against master plan; if possible, draft contingency plans for critical situations such as inclement weather, speaker cancellation, power/internet outages, global pandemics, etc.
Draft remarks or bullet points for Dean/director if needed.
Review and finalize event run of show.
Finalize PowerPoint deck including all speaker slides and/or audio-visual content for event, if applicable.
Brief host(s), greeter(s), volunteer(s) on their individual role, responsibilities, as well as any timelines.
Finalize your seating plan and produce name tags (2-3 days before event).
Continue monitoring need for additional mini-bio's of VIPs.
Gather any promotional material and signage for use at event.
Create post-event survey (i.e., what do you want to learn from attendees).
| Venue | Provide final registration numbers to caterer.
Send list of attendees to venue if security check is required.
If appropriate, ensure speaking materials (speeches, moderator questions, etc.) are printed and placed and/or distributed.
Do a final registration check, including name badges and registration list – depending on the registration deadline, this may not be possible until a few days before the event, however try to complete as early as possible.
Inform IT of any room layout changes for line-of-sight of cameras and for microphones.
| MarCom | Consult w/MarCom if necessary to identify important photo ops. and/or interview opportunities with any presenters, VIPs, guests, etc.; repeat process with any known reporter(s) and/or photographer(s).
1-3 DAYS | Venue | Ensure there are enough outlets - if not, bring power strips for attendees and your registration team.
Check with venue on wi-if accessibility, strength, password etc.
Check all necessary event supplies/needs such as easels and markers; ensure registration and media tables are prepared with branded table linens or runners, and equiped with items such as blank nametags and lanyards, paper, pens, tape, stapler, etc.; print nametags if not completed yet.
Ensure all signage is in place - promotional/branded banners in the event space, as well as around the venue including common spaces, rest rooms, parking, Wi-Fi password, etc.
| Admin. | Provide formal briefing for Dean/designee including pertinent information at a glance - date, time, location, run-of-show; supplementing the brief should be a copy of the attendee list, relevant mini bios, parking information, contact info for event staff, and any other appropriate info.
Ensure you have copies of all instructions, directions, phone numbers, keys, extra parking permit or tickets for VIP guests, seating charts, guest lists, etc., with you.
Send logistics email to all speakers and VIPs; send reminder email to all registrants - include remote access link if part/entire of event is virtual.
| IT | Ensure all A/V equipment is set up and working properly.
| MarCom | Confirm media attendance.
EVENT DAY | Host & Troubleshoot | Arrive on site early enough to ensure proper set-up of the event.
| IT | Perform sound checks, seat locations, lighting, microphone rigging and explanations.
Test audio-visual presentation (powerpoint deck, video content, etc.) if applicable
Ensure promo items, gifts, plaques, awards, certificates, etc., are on-site.
Check in with each volunteer or point person regarding their readiness.
Check in with catering; greet any sponsors and/or their guests to ensure everything is as it should be relative to their sponsorship.
Assist sponsors, speakers, and other teams as needed.
Greet attendees (w/ a smile - in many cases you may be their first contact with, or impression of, UConn!); be sure to acknowledge any VIPs in attendance, and alert School administrators to their presence as appropriate.
Upon event closure and exit, be sure to leave the space as requested or contracted.
POST-EVENT | Debrief & Closure | General check-in with venue; ensure nothing was left behind; begin returning items rented or borrowed.
Send out event feedback survey within 24 hours of event.
Debrief and recap changes/suggestions for next year or next event - include key stakeholders (Facilities, IT, MarCom, Development, and others as needed) to discuss issues experienced and lessons learned.
Send thank-you notes, emails, and/or acknowledgement letters to:
> Sponsors (may need to consult with Development or other sponsor connection)
> Speakers/presenters
> Donors (in consultation with Development Office/Foundation)
> Volunteers and other appropriate staff, students, etc.
> Media
| MarCom | Share event highlights on social media and other channels; coordinate with MarCom if appropriate.
Schedule date for delivery of photos/videos.
Update website(s), replacing any pre-event promo(s) with post-event highlights.
| Financial (Budget) | Gather all receipts, final invoices, official documentation, final registration data, etc.; update and reconcile budget, consulting with fiscal designee as necessary.
Submit an RFD (request for disbursement) to the Foundation for alcohol consumed at event, consulting your fiscal designee if necessary.
Submit all invoices to fiscal designee for payment - be sure to attach attendance record and/or printed program or agenda if required.
| IT | If IT hosted virtual event, request recording link and attendee list.
Distribute recording link to appropriate audience(s).

## Points of Contact
POINTS OF CONTACT | Development | Sue Kramer (skramer@foundation.uconn.edu); Michael Van Sambeck (mvansambeck@foundation.uconn.edu)
| E&EA | Michael Deotte (michael.deotte@uconn.edu); Meg Warren (meg.warren@uconn.edu)
| Fiscal | Rachel Greene (rachel.s.greene@uconn.edu); Carleen Morneau (carleen.morneau@uconn.edu)
| ITS | Mat Krest (mat.krest@uconn.edu); Alex DelCampo (alex.delcampo@uconn.edu)
| MarCom | Melissa Ferrigno (melissa.ferrigno@uconn.edu); Bill Eyre (bill.eyre@uconn.edu); Scott Slater (scott.slater.3@uconn.edu)
| Facilities / GBLC | Facilities/Ops: Misty Solomon-GBLC only (misty.sorensen@uconn.edu); John Rhoads (john.rhoads@uconn.edu)
| Facilities / Hartford Times | Kim Schwartz (Hartford.eventservices@uconn.edu)
| Facilities / Stamford | Kathy Harrison (kathy.harrison@uconn.edu)
| Facilities / Storrs / BUSN Building | Rebecca Vicki (Deangen1.business@uconn.edu)
| Facilities / Storrs / Other Bldg's | University Events & Conference Services | The University Events and Conference services website contains a list of venues on the Storrs campus. However, University Events and Conference Services is only responsible for reservations for the Rome Commons Ballroom, Dodd Center, UConn Bookstore, and Wilbur Cross North Reading Room as well as the primary contact for any non-UConn entity wishing to host a program at UConn. To inquire about availability of these spaces, email reservations@uconn.edu. Be sure to include the name of the space you are requesting. For Storrs campus locations not coordinated by University Events and Conference Services, please go to directly to the websites for those locations for event information.
| Facilities / Waterbury | If not MBA or Ugrad, contact John Rhoads (john.rhoads@uconn.edu)